## Slide 1
Office Move
Team Project 2
Presented by Group C

## Slide 2
Group Members
Office Move
Andrea VanHorn
Vincent Mutungi
Rodrigo Balmaceda
Mohammed Rashed

## Slide 3
Overview
Objective: Relocate 70 employees & 3 executives to a new 4-story building by December 24, 2024, with minimal disruption.
Scope: 74 offices (70 standard, 4 executive), 5 conference rooms, 4 assistant desks.
Full-spec setup: 3 chairs/office, executive suites, IT systems (54 PCs, 16 docking stations, 3 printers, 3 copiers).
Budget: $153,350 (approved increase of $13,350).
Timeline: November 18–December 24, 2024 (23 workdays).
Team Expectations: Coordinate 2 furniture & 2 IT crews for concurrent tasks (e.g., T011, T043 on 11/26).
Manage 267h furniture, 272h IT, and 22 moves within budget and timeline.
Mitigate risks (e.g., material delays, IT issues) using Smartsheet and contingency plans.
Outcomes: Completed on time (T131: Move Executives, 12/24/2024).
Full functionality for all divisions, within budget using $5,000 contingency.

## Slide 4
How We Solved It: Ensuring Project Success
  Budget Constraint: Initial $140,000 limit; $13,350 shortfall for full-spec ($153,350).
  Planned chair reduction (42 offices) to $139,700 until budget increase approved.
  Challenge: Crew Coordination Delays (e.g., T013 delayed 2h on 11/27/2024).
  Solution: Appointed a crew coordinator; held daily briefings to align 2 furniture & 2 IT crews, ensuring concurrent tasks (e.g., T015, T016 on 11/28) started on time.
  Challenge: Material Delivery Delays (e.g., Floor 1 desks delayed 11/22/2024).
  Solution: Used $2,000 from $5,000 contingency to expedite delivery; implemented staged delivery (Floor 1 by 11/25, Floor 4 by 12/09).
  Challenge: IT Integration Issues (e.g., docking station failure, T024 on 11/27/2024).
  Solution: Allocated 2h for debugging within 8h/day; mandated pre-testing for Floors 2–4 (e.g., T058, T096), ensuring smooth setups.
  Challenge: Cost Overruns (e.g., $3,000 copier repair, T109 on 12/02/2024).
  Solution: Negotiated cost split with vendor ($1,500 each); used $1,500 from contingency, staying within $153,350 budget.
  Outcome: Delivered full-spec scope (3 chairs/office, 74 offices) by 12/24/2024.

## Slide 5
Project Schedule: Key Milestones and Timeline
  Timeline: November 18–December 24, 2024 (23 workdays).
  Initiation Phase (11/18–11/20):
11/18: Confirmed building availability (T002).
11/20: Notified contractors (T004).
  Planning Phase (11/21–11/25):
11/21: Drafted office assignments (T006).
11/25: Notified employees of move plan (T008).
  Launch Phase (11/26–12/24):
11/26: Started furniture installation (T011, T043: Floors 1–2).
11/27: Began IT setup (T024, T058: Floors 1–2).
11/28: Initiated employee moves (T037, T073: Marketing, Sales).
12/04: Completed Floors 1–2 (T041, T079: Moves).
12/12: Finished Floor 3 furniture & IT (T094, T109).
12/16: Completed Floor 4 setups (T124, T129: Conference, IT).
12/24: Finalized executive moves (T131: Floor 4).
Approach: Used 2 furniture & 2 IT crews for concurrent tasks, tracked via Smartsheet.

## Slide 6
Constraints and Risks
Constraints:
  Initial Budget: $140,000 (required $153,350, approved increase of $13,350).
  Timeline: 23 workdays (11/18–12/24/2024), no-overdue deadline.
  Crew Limits: 2 furniture & 2 IT crews, 8h/day, no overtime.
  Dependencies: Furniture → IT → Moves (e.g., T024:T011FS, T037:T024FS).
Key Risks:
  Crew Coordination Delays: Delayed T013 by 2h on 11/27 (Medium risk).
  Material Delays: Floor 1 desks late on 11/22 (Medium risk).
  IT Issues: Docking station failure, T024 on 11/27 (Medium risk).
  Cost Overruns: $3,000 copier repair, T109 on 12/02 (High risk post-mitigation).
Mitigation:
Used crew coordinator, contingency fund ($5,000), pre-tested IT, tracked via Smartsheet.

## Slide 7
Lessons Learned
Successes:
  Completed on time (12/24/2024), full-spec scope.
  Managed within $153,350 using $5,000 contingency.
Challenges:
  Crew delays (T013, 11/27): Added coordinator, briefings.
  Material delays (11/22): Expedited delivery, staged plan.
Takeaways:
  Concurrent tasks need robust coordination.
  Pre-test IT to avoid integration issues.
Recommendations:
  Allocate 5% contingency budget ($7,667).
  Schedule deliveries outside holiday season.

## Slide 8
Operational Impact and Stakeholder Feedback
Operational Impact:
  Zero downtime: Operations resumed 12/26/2024.
  Full functionality: Marketing (13 docking stations), Sales (18 PCs) fully operational.
  Employee satisfaction: 90% reported seamless transition (12/26 survey).
Stakeholder Feedback:
  Director: “Impressed with on-time delivery.”
  Division Heads: Requested more pre-move updates.
Improvement Area:
  Enhance employee communication: Add Q&A sessions 1 month prior.
Recognition:
  Crew Coordinator: Ensured concurrent task success.
  IT Team Lead: Resolved docking issues swiftly.

## Slide 9
Thank
You