### Constraints List

1. Time

- Constraint: Firm deadline of December 24, 2024, for no-overdue schedule.

- Effect: Compressed timeline necessitates parallel task execution using two crews per function; delays could result in business downtime in January 2025.

2. Cost

- Constraint: $140,000 budget cap versus projected cost of $153,350.

- Effect: Requires cost-reduction strategies (furniture item cuts) or budget increase; affects decision-making on resource allocation and furnishings.

3. Scope

- Constraint: Complete furnishing and IT setup for 74 offices, 5 conference rooms, and 4 assistant desks.

- Effect: Any changes to remain within budget must carefully reduce scope without impairing functionality (eliminating chairs in 42 offices).

4. Quality

- Constraint: Expectation of full functionality and readiness by move-in.

- Effect: Reducing office furnishings could diminish user satisfaction and brand image, compromising perceived project quality.

5. Resources

- Constraint: Limited to 2 furniture crews and 2 IT crews (no overtime allowed).

- Effect: Crew availability must be tightly scheduled to ensure dependencies are met (furniture → IT → moves); inflexible labor resources could constrain progress.

6. Risks

- Constraint: Dependency sequencing (e.g., furniture must precede IT, which precedes moves).

- Effect: Any delay in preceding tasks cascades through dependent activities, increasing risk of missing the target completion date.

7. Other Constraints

- Building Availability: Must be confirmed and accessible starting November 18, 2024.

- Effect: Delay in site readiness would defer the entire schedule.

- No Additional Move Costs Allowed: Employee moves are zero-cost.

- Effect: Limits ability to add support for logistical complexity unless external resources are reallocated.

# Office Move Project: Constraints Overview

| Constraint | Category | Impact |
| --- | --- | --- |
| 🕒 | Time | Deadline of December 24, 2024, limits flexibility. Requires two crews per type and strict adherence to task dependencies. Delays risk January downtime. |
| 💰 | Cost | Target budget is $140,000, but project estimates reach $153,350. Requires cuts (removing chairs) or justification for a 9.5% increase. |
| 📦 | Scope | Full installation for 74 offices, 5 conference rooms, and 4 desks. Scope reduction (chairs) risks operational readiness. |
| 🏅 | Quality | Expected high standards for office setup. Chair reduction may hurt employee satisfaction and affect external perceptions during open house. |
| 🛠️ | Resources | Limited to 2 furniture crews and 2 IT crews, with 8-hour days and no overtime. Rigid crew limits increase pressure on schedule efficiency. |
| ⚠️ | Risks | Task dependencies (furniture → IT → moves) create cascading risk. Any delay in earlier tasks affects the entire schedule. |
| 🏢 | Other | Building must be ready by November 18, 2024. Employee moves incur no cost, restricting flexibility for unexpected logistics needs. |