# Office Move Schedule Report

Prepared for: Project Stakeholders

Date: April 17, 2025

Prepared by: Project Management Team

# Executive Summary

This report presents two schedules for the office move to the new building: an overdue schedule (extending to January 24, 2025) and a no-overdue schedule (completed by December 24, 2024). Both schedules adhere to the provided parameters, covering furniture and IT installation for 74 offices (70 standard, 4 executive), 5 conference rooms, and 4 executive assistant desks, with employee moves at no cost. The cost for both schedules is identical at $153,350, but the no-overdue schedule requires two furniture crews and two IT crews to meet the deadline December 29, 2024, avoiding business downtime. To align with a $140,000 budget, we recommend reducing furniture scope by removing two additional chairs ($325 each) from 42 standard offices, lowering the no-overdue schedule cost to $139,700 while maintaining completion by December 24, 2024.

# Project Overview

The office move involves relocating 70 employees across six divisions (Operations: 18, Distribution: 8, Accounting: 7, Marketing: 13, Sales: 18, HR: 6) and 3 executives to a new four-story building. The layout includes:

- Floor 1: 20 offices (13 Marketing, 7 Accounting), 1 conference room.

- Floor 2: 25 offices (18 Sales, 7 Operations), 1 conference room.

- Floor 3: 25 offices (11 Operations, 8 Distribution, 6 HR), 1 conference room.

- Floor 4: 4 offices (3 Executives, 1 empty), 2 conference rooms, 4 assistant desks.

# Scope:

- Furniture: Install desks, chairs, and conference tables (267 hours total).

- IT: Set up PCs, laptops with docking stations, printers, and copiers (272 hours total).

- Moves: Relocate 70 employees and equipment (22 tasks, no cost).

- Constraints: One crew per type in overdue schedule; two crews per type in no-overdue schedule; 8 hours/day, no overtime; furniture precedes IT, IT precedes moves.

Objective: Complete the move by December 29, 2024, within a $140,000 budget, minimizing disruption.

# Schedule Details

## Overdue Schedule

### Timeline:

November 18, 2024–January 24, 2025 (~44 workdays, excluding weekends, December 25).

- Initiation: November 18–20, 2024 (3 days, completed).

- Planning: November 21–25, 2024 (3 days, completed).

- Launch: November 26, 2024–January 24, 2025 (~38 workdays).

### Crews:

Furniture: 1 crew (267 hours, ~34 days).

IT: 1 crew (272 hours, ~34 days).

Moves: 1 team (0 cost).

### Tasks:

83 total (6 Initiation/Planning, 77 Launch: 37 furniture, 34 IT, 22 moves).

Progress by December 29, 2024 (~29 workdays):

Furniture: Floor 1 complete (20 offices, 1 conference room), Floor 2: ~22 offices.

IT: Floor 1 complete (20 offices, printer, copier), Floor 2: ~20 offices.

Moves: Floor 1 complete (5 tasks), Floor 2: ~5 tasks.

Incomplete: Floor 2 (3 offices, printer, copier, 2 moves), all Floor 3 and Floor 4 tasks (~15 workdays overdue).

### Key Dates:

Start: November 18, 2024 (T002: Confirm Building Availability).

End: January 24, 2025 (T131: Move Executives to Floor 4).

- Dependencies: Furniture precedes IT (e.g., T024: IT Floor 1 Offices 1-2 depends on T011FS); IT precedes moves (e.g., T037: Move Marketing depends on T024FS; T025FS).

## No-Overdue Schedule

### Timeline:

November 18–December 24, 2024 (23 workdays, excluding weekends, December 25).

- Initiation: November 18–20, 2024 (3 days, completed).

- Planning: November 21–25, 2024 (3 days, completed).

- Launch: November 26–December 24, 2024 (17 workdays).

### Crews:

Furniture: 2 crews (~134h/crew, ~17 days).

IT: 2 crews (~136h/crew, ~18 days).

Moves: 1 team (0 cost).

### Tasks:

83 total (same as overdue).

Progress:

Furniture: All floors complete by ~December 18 (T124: Floor 4 Conference Room 2).

IT: All floors complete by ~December 24 (T129: Floor 4 Executive Office 4).

Moves: All complete by December 24 (T131: Move Executives).

### Key Dates:

Start: November 18, 2024 (T002).

End: December 24, 2024 (T131).

Dependences: Same as overdue, with parallel crew assignments (e.g., Furniture Crew 1: Floor 1:1-2, Crew 2: Floor 1:3-4).

# Cost Analysis

Costs are calculated per the parameters provided, with no additional expenses (e.g., transportation, insurance).

## Overdue Schedule Costs

Furniture: $130,950

Materials: $122,940

Standard offices: 70 × $1,300 = $91,000.

Conference rooms: 5 × $2,400 = $12,000.

Executive offices: 4 × $4,010 = $16,040.

Assistant desks: 4 × $975 = $3,900.

Labor: 267h × $30/h = $8,010 (70 offices × 3h, 5 conference rooms × 5h, 4 executive offices × 8h).

IT: $22,400

Standard offices: 54 × $200 = $10,800 (3h each; Accounting: 7, Sales: 18, Operations: 15, Distribution: 8, HR: 6).

Docking offices: 16 × $300 = $4,800 (4h each; 13 Marketing, 3 Executives).

Printers: 3 × $200 = $600 (3h each, Floors 1–3).

Copiers: 3 × $200 = $600 (3h each, Floors 1–3).

Executive offices: 4 × $1,400 = $5,600 (7h each).

Moves: $0 (22 tasks, per instruction).

Total: $130,950 + $22,400 = $153,350.

## No-Overdue Schedule Costs

Furniture: $130,950 (same materials and labor as overdue, split across 2 crews).

IT: $22,400 (same tasks, split across 2 crews).

Moves: $0.

Total: $153,350.

## Cost Comparison

Difference: $0. Both schedules cost $153,350, as furniture is charged per hour ($30/h), IT per task ($200–$1,400), and moves are free, regardless of crew count or timeline.

Budget Issue: Both exceed the $140,000 target by $13,350.

Schedule Advantage: No-overdue saves ~21 workdays, avoiding January 2025 downtime, critical for business continuity.

## Cost-Cutting Recommendation

To meet the $140,000 budget while maintaining the no-overdue schedule (ending December 24, 2024), we propose the following tweak:

Remove two additional chairs ($325 each) from 42 standard offices

(e.g., 7 Accounting, 18 Sales, 17 Operations across Floors 1–3).

Savings: 42 × $325 = $13,650.

New Furniture Cost:

Standard offices: 42 × $975 (desk + chair) = $40,950 + 28 × $1,300 = $36,400 = $77,350.

Conference rooms: $12,000 (unchanged).

Executive offices: $16,040.

Assistant desks: $3,900.

Labor: $8,010 (267h unchanged).

Total Furniture: $77,350 + $12,000 + $16,040 + $3,900 + $8,010 = $117,300.

New Total Cost: $117,300 (furniture) + $22,400 (IT) + $0 (moves) = $139,700.

Budget Fit: $140,000 – $139,700 = $300 surplus.

- Schedule Impact: None. Furniture hours (267h, 2 crews, ~17 days, T011–T124) and IT hours (272h, 2 crews, ~18 days, T024–T129) remain unchanged, completing by December 24, 2024 (T131). Dependencies (e.g., T024FS:T011, T037:T024FS; T025FS) are unaffected, as chair removal doesn’t alter labor or task sequence.

- Operational Impact: 42 offices have one chair instead of three, sufficient for single occupants (e.g., Accounting, Sales). Desks, PCs, docking stations, printers, copiers, and executive/conference setups are preserved, ensuring full functionality.

- Rationale: Targets non-essential seating in non-client-facing areas, minimizing disruption while meeting budget and deadline.

## Alternative Considered:

Skip furniture and IT for the empty executive office (T122, T129).

Savings: $4,010 + 8h × $30 + $1,400 = $5,650.

Additional cut: Remove chairs from ~24 offices ($7,800).

Total: $139,900.

Downside: Leaves Floor 4 is partially incomplete, less desirable than uniform chair reduction.

# Recommendation

The current office move plan requires $153,350 to meet all specifications (furniture, IT, labor), exceeding the $140,000 budget by $13,350. While cost-cutting measures (e.g., reducing chairs in 42 offices) can align with the budget, this compromises employee comfort and operational readiness.

## Justification for Increase:

1. Employee Productivity & Morale:

Standard offices are designed for  3 chairs (1 occupant, 2 guests). Reducing to 1 chair disrupts collaboration and client meetings.

2. Brand Image:

A partially furnished office may convey instability to visitors ahead of the Dec 30 open house.

3. Future Cost Avoidance:

Procuring chairs later incurs additional delivery/installation fees (~$1,500).

## Proposed Budget Adjustment:

Total Required:$153,350 (includes 4 executive offices, full IT, and all furniture).

- Increase Needed: $13,350 (9.5% over budget).

Mitigation Options:

- Repurpose Funds: Use Q1 2025 facilities budget to offset ~$6,000.

- Phase IT Costs: Delay non-critical IT upgrades (e.g., copier backups) until January.

# Conclusion & Next Steps

## Conclusion:

The no-overdue schedule (completing by December 24, 2024) is achievable at $153,350 while maintaining full office standards. Though chair reductions can fit the $140,000 budget, they risk employee satisfaction and operational efficiency. We recommend approving the budget increase to ensure a seamless transition.

## Next Steps:

1. Await budget decision (increase approval or chair reduction).

2. If approved:

- Finalize contracts with furniture/IT vendors.

- Update Smartsheet with full specifications.

3. If denied:

- Implement chair reductions ($139,700 plan).

- Notify affected teams (Accounting, Sales, Operations) of temporary seating changes.

4. Proceed with move schedule, monitoring crew productivity to avoid delays.

Final Deliverables:

- Updated budget tracker (shared via SmartSheet).