## Task Sheet 5(Corrected)
Task ID | Task Name | Start Date | End Date | Duration | Predecessors | Assigned To | Health | Status | Notes | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18
T001 | Initiation Phase
T002 | Confirm Building Availability | 2024-11-18 | 2024-11-18 | 1d |  | Project Manager | On Track | Completed | Verify with building management
T003 | Review Contractor Contracts | 2024-11-19 | 2024-11-19 | 1d | T002 | Project Manager | On Track | Completed | Ensure scope and constraints clear
T004 | Notify Furniture and IT Contractors | 2024-11-20 | 2024-11-20 | 1d | T003 | Project Manager | On Track | Completed | Share preliminary schedule with two crews each
T005 | Planning Phase
T006 | Draft Office Assignments | 2024-11-21 | 2024-11-21 | 1d | T004 | Project Manager | On Track | Completed | Assign 70 employees: F1 (13M | 7A) | F2 (18S | 7O) | F3 (11O | 8D | 6H) | F4 (3E | 1 empty)
T007 | Develop Preliminary Schedule | 2024-11-22 | 2024-11-22 | 1d | T006 | Project Manager | On Track | Completed | Two furniture and IT crews to meet 12/29 deadline
T008 | Notify Employees of Move Plan | 2024-11-25 | 2024-11-25 | 1d | T007 | HR Team | On Track | Completed | Send move details to staff
T009 | Launch Phase
T010 | Floor 1: Furniture Installation
T011 | Furniture: Floor 1 Offices 1-2 (Marketing) | 2024-11-26 | 2024-11-26 | 1d | T008 | Furniture Crew 1 | On Track | Not Started | 6h (3h each)
T012 | Furniture: Floor 1 Offices 3-4 (Marketing) | 2024-11-26 | 2024-11-26 | 1d | T008 | Furniture Crew 2 | On Track | Not Started | 6h
T013 | Furniture: Floor 1 Offices 5-6 (Marketing) | 2024-11-27 | 2024-11-27 | 1d | T011 | Furniture Crew 1 | On Track | Not Started | 6h
T014 | Furniture: Floor 1 Offices 7-8 (Marketing) | 2024-11-27 | 2024-11-27 | 1d | T012 | Furniture Crew 2 | On Track | Not Started | 6h
T015 | Furniture: Floor 1 Offices 9-10 (Marketing) | 2024-11-28 | 2024-11-28 | 1d | T013 | Furniture Crew 1 | On Track | Not Started | 6h
T016 | Furniture: Floor 1 Offices 11-12 (Marketing) | 2024-11-28 | 2024-11-28 | 1d | T014 | Furniture Crew 2 | On Track | Not Started | 6h
T017 | Furniture: Floor 1 Office 13 (Marketing) | 2024-11-29 | 2024-11-29 | 1d | T015 | Furniture Crew 1 | On Track | Not Started | 3h
T018 | Furniture: Floor 1 Offices 14-15 (Accounting) | 2024-11-29 | 2024-11-29 | 1d | T016 | Furniture Crew 2 | On Track | Not Started | 6h
T019 | Furniture: Floor 1 Offices 16-17 (Accounting) | 2024-12-02 | 2024-12-02 | 1d | T017 | Furniture Crew 1 | On Track | Not Started | 6h
T020 | Furniture: Floor 1 Offices 18-19 (Accounting) | 2024-12-02 | 2024-12-02 | 1d | T018 | Furniture Crew 2 | On Track | Not Started | 6h
T021 | Furniture: Floor 1 Office 20 (Accounting) | 2024-12-03 | 2024-12-03 | 1d | T019 | Furniture Crew 1 | On Track | Not Started | 3h
T022 | Furniture: Floor 1 Conference Room | 2024-12-03 | 2024-12-03 | 1d | T020 | Furniture Crew 2 | On Track | Not Started | 5h
T023 | Floor 1: IT Installation
T024 | IT: Floor 1 Offices 1-2 (Marketing) | 2024-11-27 | 2024-11-27 | 1d | T011FS | IT Crew 1 | On Track | Not Started | 8h (4h each | docking)
T025 | IT: Floor 1 Offices 3-4 (Marketing) | 2024-11-27 | 2024-11-27 | 1d | T012FS | IT Crew 2 | On Track | Not Started | 8h (4h each | docking)
T026 | IT: Floor 1 Offices 5-6 (Marketing) | 2024-11-28 | 2024-11-28 | 1d | T013FS | IT Crew 1 | On Track | Not Started | 8h (4h each | docking)
T027 | IT: Floor 1 Offices 7-8 (Marketing) | 2024-11-28 | 2024-11-28 | 1d | T014FS | IT Crew 2 | On Track | Not Started | 8h (4h each | docking)
T028 | IT: Floor 1 Offices 9-10 (Marketing) | 2024-11-29 | 2024-11-29 | 1d | T015FS | IT Crew 1 | On Track | Not Started | 8h (4h each | docking)
T029 | IT: Floor 1 Offices 11-12 (Marketing) | 2024-11-29 | 2024-11-29 | 1d | T016FS | IT Crew 2 | On Track | Not Started | 8h (4h each | docking)
T030 | IT: Floor 1 Office 13 (Marketing) | 2024-12-02 | 2024-12-02 | 1d | T017FS | IT Crew 1 | On Track | Not Started | 4h (docking)
T031 | IT: Floor 1 Offices 14-15 (Accounting) | 2024-12-02 | 2024-12-02 | 1d | T018FS | IT Crew 2 | On Track | Not Started | 6h (3h each | standard)
T032 | IT: Floor 1 Offices 16-17 (Accounting) | 2024-12-03 | 2024-12-03 | 1d | T019FS | IT Crew 1 | On Track | Not Started | 6h (3h each | standard)
T033 | IT: Floor 1 Offices 18-19 (Accounting) | 2024-12-03 | 2024-12-03 | 1d | T020FS | IT Crew 2 | On Track | Not Started | 6h (3h each | standard)
T034 | IT: Floor 1 Office 20 (Accounting) | 2024-12-04 | 2024-12-04 | 1d | T021FS | IT Crew 1 | On Track | Not Started | 3h (standard)
T035 | IT: Floor 1 Printer and Copier | 2024-12-04 | 2024-12-04 | 1d | T022FS | IT Crew 2 | On Track | Not Started | 6h (3h each)
T036 | Floor 1: Employee Moves
T037 | Move: 4 Marketing to Floor 1 Offices 1-4 | 2024-11-28 | 2024-11-28 | 1d | T024FS;T025FS | Moving Team | On Track | Not Started | Offices ready by 11/27
T038 | Move: 4 Marketing to Floor 1 Offices 5-8 | 2024-11-29 | 2024-11-29 | 1d | T026FS;T027FS | Moving Team | On Track | Not Started | Offices ready by 11/28
T039 | Move: 5 Marketing to Floor 1 Offices 9-13 | 2024-12-03 | 2024-12-03 | 1d | T028FS;T029FS;T030FS | Moving Team | On Track | Not Started | Offices ready by 12/02
T040 | Move: 4 Accounting to Floor 1 Offices 14-17 | 2024-12-04 | 2024-12-04 | 1d | T031FS;T032FS | Moving Team | On Track | Not Started | Offices ready by 12/03
T041 | Move: 3 Accounting to Floor 1 Offices 18-20 | 2024-12-05 | 2024-12-05 | 1d | T033FS;T034FS | Moving Team | On Track | Not Started | Offices ready by 12/04
T042 | Floor 2: Furniture Installation
T043 | Furniture: Floor 2 Offices 1-2 (Sales) | 2024-12-04 | 2024-12-04 | 1d | T021 | Furniture Crew 1 | On Track | Not Started | 6h
T044 | Furniture: Floor 2 Offices 3-4 (Sales) | 2024-12-04 | 2024-12-04 | 1d | T022 | Furniture Crew 2 | On Track | Not Started | 6h
T045 | Furniture: Floor 2 Offices 5-6 (Sales) | 2024-12-05 | 2024-12-05 | 1d | T043 | Furniture Crew 1 | On Track | Not Started | 6h
T046 | Furniture: Floor 2 Offices 7-8 (Sales) | 2024-12-05 | 2024-12-05 | 1d | T044 | Furniture Crew 2 | On Track | Not Started | 6h
T047 | Furniture: Floor 2 Offices 9-10 (Sales) | 2024-12-06 | 2024-12-06 | 1d | T045 | Furniture Crew 1 | On Track | Not Started | 6h
T048 | Furniture: Floor 2 Offices 11-12 (Sales) | 2024-12-06 | 2024-12-06 | 1d | T046 | Furniture Crew 2 | On Track | Not Started | 6h
T049 | Furniture: Floor 2 Offices 13-14 (Sales) | 2024-12-09 | 2024-12-09 | 1d | T047 | Furniture Crew 1 | On Track | Not Started | 6h
T050 | Furniture: Floor 2 Offices 15-16 (Sales) | 2024-12-09 | 2024-12-09 | 1d | T048 | Furniture Crew 2 | On Track | Not Started | 6h
T051 | Furniture: Floor 2 Offices 17-18 (Sales) | 2024-12-10 | 2024-12-10 | 1d | T049 | Furniture Crew 1 | On Track | Not Started | 6h
T052 | Furniture: Floor 2 Offices 19-20 (Operations) | 2024-12-10 | 2024-12-10 | 1d | T050 | Furniture Crew 2 | On Track | Not Started | 6h
T053 | Furniture: Floor 2 Offices 21-22 (Operations) | 2024-12-11 | 2024-12-11 | 1d | T051 | Furniture Crew 1 | On Track | Not Started | 6h
T054 | Furniture: Floor 2 Offices 23-24 (Operations) | 2024-12-11 | 2024-12-11 | 1d | T052 | Furniture Crew 2 | On Track | Not Started | 6h
T055 | Furniture: Floor 2 Office 25 (Operations) | 2024-12-12 | 2024-12-12 | 1d | T053 | Furniture Crew 1 | On Track | Not Started | 3h
T056 | Furniture: Floor 2 Conference Room | 2024-12-12 | 2024-12-12 | 1d | T054 | Furniture Crew 2 | On Track | Not Started | 5h
T057 | Floor 2: IT Installation
T058 | IT: Floor 2 Offices 1-2 (Sales) | 2024-12-05 | 2024-12-05 | 1d | T043FS | IT Crew 1 | On Track | Not Started | 7h (4h docking 3h standard)
T059 | IT: Floor 2 Offices 3-4 (Sales) | 2024-12-05 | 2024-12-05 | 1d | T044FS | IT Crew 2 | On Track | Not Started | 6h (3h each standard)
T060 | IT: Floor 2 Offices 5-6 (Sales) | 2024-12-06 | 2024-12-06 | 1d | T045FS | IT Crew 1 | On Track | Not Started | 6h (3h each standard)
T061 | IT: Floor 2 Offices 7-8 (Sales) | 2024-12-06 | 2024-12-06 | 1d | T046FS | IT Crew 2 | On Track | Not Started | 6h (3h each standard)
T062 | IT: Floor 2 Offices 9-10 (Sales) | 2024-12-09 | 2024-12-09 | 1d | T047FS | IT Crew 1 | On Track | Not Started | 6h (3h each standard)
T063 | IT: Floor 2 Offices 11-12 (Sales) | 2024-12-09 | 2024-12-09 | 1d | T048FS | IT Crew 2 | On Track | Not Started | 6h (3h each standard)
T064 | IT: Floor 2 Offices 13-14 (Sales) | 2024-12-10 | 2024-12-10 | 1d | T049FS | IT Crew 1 | On Track | Not Started | 6h (3h each standard)
T065 | IT: Floor 2 Offices 15-16 (Sales) | 2024-12-10 | 2024-12-10 | 1d | T050FS | IT Crew 2 | On Track | Not Started | 6h (3h each standard)
T066 | IT: Floor 2 Offices 17-18 (Sales) | 2024-12-11 | 2024-12-11 | 1d | T051FS | IT Crew 1 | On Track | Not Started | 6h (3h each standard)
T067 | IT: Floor 2 Offices 19-20 (Operations) | 2024-12-11 | 2024-12-11 | 1d | T052FS | IT Crew 2 | On Track | Not Started | 6h (3h each standard)
T068 | IT: Floor 2 Offices 21-22 (Operations) | 2024-12-12 | 2024-12-12 | 1d | T053FS | IT Crew 1 | On Track | Not Started | 6h (3h each standard)
T069 | IT: Floor 2 Offices 23-24 (Operations) | 2024-12-12 | 2024-12-12 | 1d | T054FS | IT Crew 2 | On Track | Not Started | 6h (3h each standard)
T070 | IT: Floor 2 Office 25 (Operations) | 2024-12-13 | 2024-12-13 | 1d | T055FS | IT Crew 1 | On Track | Not Started | 3h (standard)
T071 | IT: Floor 2 Printer and Copier | 2024-12-13 | 2024-12-13 | 1d | T056FS | IT Crew 2 | On Track | Not Started | 6h (3h each)
T072 | Floor 2: Employee Moves
T073 | Move: 4 Sales to Floor 2 Offices 1-4 | 2024-12-06 | 2024-12-06 | 1d | T058FS;T059FS | Moving Team | On Track | Not Started | Offices ready by 12/05
T074 | Move: 4 Sales to Floor 2 Offices 5-8 | 2024-12-09 | 2024-12-09 | 1d | T060FS;T061FS | Moving Team | On Track | Not Started | Offices ready by 12/06
T075 | Move: 4 Sales to Floor 2 Offices 9-12 | 2024-12-10 | 2024-12-10 | 1d | T062FS;T063FS | Moving Team | On Track | Not Started | Offices ready by 12/09
T076 | Move: 4 Sales to Floor 2 Offices 13-16 | 2024-12-11 | 2024-12-11 | 1d | T064FS;T065FS | Moving Team | On Track | Not Started | Offices ready by 12/10
T077 | Move: 2 Sales 2 Operations to Floor 2 Offices 17-20 | 2024-12-12 | 2024-12-12 | 1d | T066FS;T067FS | Moving Team | On Track | Not Started | Offices ready by 12/11
T078 | Move: 4 Operations to Floor 2 Offices 21-24 | 2024-12-13 | 2024-12-13 | 1d | T068FS;T069FS | Moving Team | On Track | Not Started | Offices ready by 12/12
T079 | Move: 1 Operations to Floor 2 Office 25 | 2024-12-16 | 2024-12-16 | 1d | T070FS | Moving Team | On Track | Not Started | Office ready by 12/13
T080 | Floor 3: Furniture Installation
T081 | Furniture: Floor 3 Offices 1-2 (Operations) | 2024-12-12 | 2024-12-12 | 1d | T055 | Furniture Crew 1 | On Track | Not Started | 6h
T082 | Furniture: Floor 3 Offices 3-4 (Operations) | 2024-12-12 | 2024-12-12 | 1d | T056 | Furniture Crew 2 | On Track | Not Started | 6h
T083 | Furniture: Floor 3 Offices 5-6 (Operations) | 2024-12-13 | 2024-12-13 | 1d | T081 | Furniture Crew 1 | On Track | Not Started | 6h
T084 | Furniture: Floor 3 Offices 7-8 (Operations) | 2024-12-13 | 2024-12-13 | 1d | T082 | Furniture Crew 2 | On Track | Not Started | 6h
T085 | Furniture: Floor 3 Offices 9-10 (Distribution) | 2024-12-16 | 2024-12-16 | 1d | T083 | Furniture Crew 1 | On Track | Not Started | 6h
T086 | Furniture: Floor 3 Offices 11-12 (Distribution) | 2024-12-16 | 2024-12-16 | 1d | T084 | Furniture Crew 2 | On Track | Not Started | 6h
T087 | Furniture: Floor 3 Offices 13-14 (Distribution) | 2024-12-17 | 2024-12-17 | 1d | T085 | Furniture Crew 1 | On Track | Not Started | 6h
T088 | Furniture: Floor 3 Offices 15-16 (HR) | 2024-12-17 | 2024-12-17 | 1d | T086 | Furniture Crew 2 | On Track | Not Started | 6h
T089 | Furniture: Floor 3 Offices 17-18 (HR) | 2024-12-18 | 2024-12-18 | 1d | T087 | Furniture Crew 1 | On Track | Not Started | 6h
T090 | Furniture: Floor 3 Offices 19-20 (HR) | 2024-12-18 | 2024-12-18 | 1d | T088 | Furniture Crew 2 | On Track | Not Started | 6h
T091 | Furniture: Floor 3 Offices 21-22 (Operations) | 2024-12-19 | 2024-12-19 | 1d | T089 | Furniture Crew 1 | On Track | Not Started | 6h
T092 | Furniture: Floor 3 Offices 23-24 (Distribution) | 2024-12-19 | 2024-12-19 | 1d | T090 | Furniture Crew 2 | On Track | Not Started | 6h
T093 | Furniture: Floor 3 Office 25 (Operations) | 2024-12-20 | 2024-12-20 | 1d | T091 | Furniture Crew 1 | On Track | Not Started | 3h
T094 | Furniture: Floor 3 Conference Room | 2024-12-20 | 2024-12-20 | 1d | T092 | Furniture Crew 2 | On Track | Not Started | 5h
T095 | Floor 3: IT Installation
T096 | IT: Floor 3 Offices 1-2 (Operations) | 2024-12-13 | 2024-12-13 | 1d | T081FS | IT Crew 1 | On Track | Not Started | 7h (4h docking 3h standard)
T097 | IT: Floor 3 Offices 3-4 (Operations) | 2024-12-13 | 2024-12-13 | 1d | T082FS | IT Crew 2 | On Track | Not Started | 6h (3h each standard)
T098 | IT: Floor 3 Offices 5-6 (Operations) | 2024-12-16 | 2024-12-16 | 1d | T083FS | IT Crew 1 | On Track | Not Started | 6h (3h each standard)
T099 | IT: Floor 3 Offices 7-8 (Operations) | 2024-12-16 | 2024-12-16 | 1d | T084FS | IT Crew 2 | On Track | Not Started | 6h (3h each standard)
T100 | IT: Floor 3 Offices 9-10 (Distribution) | 2024-12-17 | 2024-12-17 | 1d | T085FS | IT Crew 1 | On Track | Not Started | 6h (3h each standard)
T101 | IT: Floor 3 Offices 11-12 (Distribution) | 2024-12-17 | 2024-12-17 | 1d | T086FS | IT Crew 2 | On Track | Not Started | 6h (3h each standard)
T102 | IT: Floor 3 Offices 13-14 (Distribution) | 2024-12-18 | 2024-12-18 | 1d | T087FS | IT Crew 1 | On Track | Not Started | 6h (3h each standard)
T103 | IT: Floor 3 Offices 15-16 (HR) | 2024-12-18 | 2024-12-18 | 1d | T088FS | IT Crew 2 | On Track | Not Started | 6h (3h each standard)
T104 | IT: Floor 3 Offices 17-18 (HR) | 2024-12-19 | 2024-12-19 | 1d | T089FS | IT Crew 1 | On Track | Not Started | 6h (3h each standard)
T105 | IT: Floor 3 Offices 19-20 (HR) | 2024-12-19 | 2024-12-19 | 1d | T090FS | IT Crew 2 | On Track | Not Started | 6h (3h each standard)
T106 | IT: Floor 3 Offices 21-22 (Operations) | 2024-12-20 | 2024-12-20 | 1d | T091FS | IT Crew 1 | On Track | Not Started | 6h (3h each standard)
T107 | IT: Floor 3 Offices 23-24 (Distribution) | 2024-12-20 | 2024-12-20 | 1d | T092FS | IT Crew 2 | On Track | Not Started | 6h (3h each standard)
T108 | IT: Floor 3 Office 25 (Operations) | 2024-12-23 | 2024-12-23 | 1d | T093FS | IT Crew 1 | On Track | Not Started | 3h (standard)
T109 | IT: Floor 3 Printer and Copier | 2024-12-23 | 2024-12-23 | 1d | T094FS | IT Crew 2 | On Track | Not Started | 6h (3h each)
T110 | Floor 3: Employee Moves
T111 | Move: 4 Operations to Floor 3 Offices 1-4 | 2024-12-16 | 2024-12-16 | 1d | T096FS;T097FS | Moving Team | On Track | Not Started | Offices ready by 12/13
T112 | Move: 3 Operations 1 Distribution to Floor 3 Offices 5-8 | 2024-12-17 | 2024-12-17 | 1d | T098FS;T099FS | Moving Team | On Track | Not Started | Offices ready by 12/16
T113 | Move: 4 Distribution to Floor 3 Offices 9-12 | 2024-12-18 | 2024-12-18 | 1d | T100FS;T101FS | Moving Team | On Track | Not Started | Offices ready by 12/17
T114 | Move: 2 Distribution 2 HR to Floor 3 Offices 13-16 | 2024-12-19 | 2024-12-19 | 1d | T102FS;T103FS | Moving Team | On Track | Not Started | Offices ready by 12/18
T115 | Move: 4 HR to Floor 3 Offices 17-20 | 2024-12-20 | 2024-12-20 | 1d | T104FS;T105FS | Moving Team | On Track | Not Started | Offices ready by 12/19
T116 | Move: 3 Operations 1 Distribution to Floor 3 Offices 21-24 | 2024-12-23 | 2024-12-23 | 1d | T106FS;T107FS | Moving Team | On Track | Not Started | Offices ready by 12/20
T117 | Move: 1 Operations to Floor 3 Office 25 | 2024-12-24 | 2024-12-24 | 1d | T108FS | Moving Team | On Track | Not Started | Office ready by 12/23
T118 | Floor 4: Furniture Installation
T119 | Furniture: Floor 4 Executive Office 1 | 2024-12-20 | 2024-12-20 | 1d | T093 | Furniture Crew 1 | On Track | Not Started | 8h; Includes assistant desk
T120 | Furniture: Floor 4 Executive Office 2 | 2024-12-20 | 2024-12-20 | 1d | T094 | Furniture Crew 2 | On Track | Not Started | 8h
T121 | Furniture: Floor 4 Executive Office 3 | 2024-12-23 | 2024-12-23 | 1d | T119 | Furniture Crew 1 | On Track | Not Started | 8h
T122 | Furniture: Floor 4 Executive Office 4 (Empty) | 2024-12-23 | 2024-12-23 | 1d | T120 | Furniture Crew 2 | On Track | Not Started | 8h
T123 | Furniture: Floor 4 Conference Room 1 | 2024-12-24 | 2024-12-24 | 1d | T121 | Furniture Crew 1 | On Track | Not Started | 5h
T124 | Furniture: Floor 4 Conference Room 2 | 2024-12-24 | 2024-12-24 | 1d | T122 | Furniture Crew 2 | On Track | Not Started | 5h
T125 | Floor 4: IT Installation
T126 | IT: Floor 4 Executive Office 1 | 2024-12-23 | 2024-12-23 | 1d | T119FS | IT Crew 1 | On Track | Not Started | 7h
T127 | IT: Floor 4 Executive Office 2 | 2024-12-23 | 2024-12-23 | 1d | T120FS | IT Crew 2 | On Track | Not Started | 7h
T128 | IT: Floor 4 Executive Office 3 | 2024-12-24 | 2024-12-24 | 1d | T121FS | IT Crew 1 | On Track | Not Started | 7h
T129 | IT: Floor 4 Executive Office 4 (Empty) | 2024-12-24 | 2024-12-24 | 1d | T122FS | IT Crew 2 | On Track | Not Started | 7h
T130 | Floor 4: Employee Moves
T131 | Move: 3 Executives to Floor 4 Offices 1-3 | 2024-12-24 | 2024-12-24 | 1d | T126FS;T127FS;T128FS | Moving Team | On Track | Not Started | Offices ready by 12/24