## Team Project 2

## Office Move

This is your team project and will consist of researching, organizing, and briefing your plan to move a company into a new office building. You are making a pitch to the VP of Operations to lead this project. Your team will turn in (at a minimum) the deliverable items listed below on the respective due dates. You will also present a 10-20 minute team briefing on your plan to the VP for Operations.

Start Project

1. In-Progress Revue (IPR) -- Due Apr 18

Deliverables for IPR:

- Project Charter

- Stakeholder Register

- Scope Statement

- Initial Schedule/WBS – not the final version, but enough of a plan and timeline to provide a framework for the organization. Please submit a project management software file (or share a sheet if using online platform).

2. Briefing and Final Product (Deliverables) Turn-In -- Due Apr 27

- All deliverables from IPR

- Completed WBS – project management software export or file

- Risk Assessment

- Communication Plan

- Presentation

- Outline the project that you were hired to do

- Demonstrate how you solved it (what did you do to make it work?)

- Discuss your schedule (when did you do what?)

- Discuss constraints/risks, lessons learned, etc.

- Provide any other information that you think is valuable.

Other important information:

Use project management software as much as possible

# Overview:

Your company has outgrown its current headquarters and is in the process of moving to a new building. You are responsible for moving the entire company. Each employee you are responsible for moving will have an individual office in the new building.

You have four floors and 74 offices to move people into. The first floor has a lobby and 20 offices. The second and third floors each have 25 offices. Each of the first three floors also has a conference room and a combination copy/break room. Each division has a director included in the total number of employees. The fourth floor is for the company’s executives. It has four offices with four executive assistant offices at each entry. In addition, there are two conference rooms on the executive floor.

# Planning:

The selection of a furniture contractor and IT contractor is complete, and they will begin work once they have your schedule. Their scope is as follows:

Furniture—Each office will have a standard desk and chair ($975) plus two additional chairs ($325). Each conference room will have a conference table ($1200) and eight chairs ($1200).

The contractor will deliver, assemble, and place the furniture in each room as directed. It takes them three hours (one crew @ $30/hr) to finish one office and five hours per conference room. They cannot work more than eight hours per day. The executive offices ($4010) require eight hours for furniture installation.

IT—Each standard office will have a PC and be linked to a network printer in the copy/break room. Each director, executive, plus everyone in the Marketing Division, has a laptop with a docking station.

The contractor will take care of all delivery and installation and work out any “bugs.” They will install a standard office in three hours ($200) and a docking station office in four hours ($300). Each floor has a network printer that will take three hours to install ($200) and each of the first three floors will have a copier that requires three hours ($200). The fourth floor has no networked printer, but it will take IT seven hours to install each executive office, including the assistant. IT will work no more than eight hours each day.

Divisions/Departments and a number of employees (including Directors) are as follows:

Operations           18

Distribution            8

Accounting             7

Marketing             13

Sales                      18

Human Resources  6

Executive Offices – Four offices located on the 4th floor of the new building, with four executive assistant desks( $975)  located outside each office.

# Instructions from the VP for Operations:

- You can start moving no earlier than November 26st (the building will be completed November 25th) and must be finished no later than December 29th. The CEO has already scheduled an open house and company New Year’s Eve Party for December 30th.

- We cannot shut down our business while we move. In other words, not all of Accounting or any other department can move at the same time. Someone must still be available for business operations.

- Provide a detailed schedule of who moves when and where so we can communicate what is happening to all of our valued team-co-family-member-employees.

The VP for Operations will want to know what you determine as the total cost for your project:

- The budget is $140,000.

- Without prior approval, you cannot schedule overtime (working more than 8 hours or weekends) (1.5x the hourly wage).

- You have to rely on one furniture crew and one IT crew unless you obtain approval.

- You cannot split an activity into more than one day, i.e., if you start furniture installation in an office, it must finish that day. You cannot use one hour at the end of one day and finish it with two hours the following morning.

- You must have at least two people from a division on the same floor. For example, you cannot leave a lonely Marketing employee mixed in with another division; you must have at least two or more from a division on a floor if they will not all fit on one floor.

- We are looking to promote a director to the fourth floor. Only three of the four executive offices will be occupied; one will be empty for now.

# Hints

- The project is designed to make you work out a schedule and spend some time optimizing the utilization of the crews. Project management software or some other way of graphically and conceptually understanding this problem will be helpful.

- You will quickly realize that time and budget could be constraints to executing this project. I am looking for creative ways of solving some of the problems. Once you understand the problem, discuss it with the team and come up with solutions (and asks), you can email me what you would like to do to make this project work.

- In terms of the other deliverables, such as the project charter, stakeholder register, etc., they are going to be the same documents that we used in Project 1, but with different content. Although the context is different, we are still managing a project.